## Instructions
16 WEEK TRADE SHOW ACTION PLAN
To give yourself enough time to execute a productive and profitable exhibiting program, ideally,
you should be contracted and start planning about 16 weeks before the event. Logistics play a large
role in the success of your trade show program. Logistics ensure you get to the show. Strategy
ensures you get FROM the show. To get the most out of your investment in trade shows,
it's critical to balance logistics with strategy. A lot of exhibit managers spend 95% of their
pre-show time on getting the space, the booth, the products and the people there, into, up, down,
and back from the show. They spend 5% or less on the critical strategic issues that determine
whether the show ends up as an expensive appearance or profitable investment.
This Trade Show Action Plan is designed to incorporate logistical tasks as well as five critical
exhibiting strategic factors:
1. | Outcomes - your exhibit program should accomplish two things: visibly and directly support
core business objectives, and deliver measurable financial value, beyond cost.
2. | Selective Attraction - If you don’t get face to face with enough of the right attendees, your
exhibiting program is NOT going to deliver results.
3. | Managing the Visitor Experience - Attendees go to shows to DO, SEE and LEARN a lot more
than they can on your website. Among all the exhibitors they could visit, why should they visit
your exhibit? There are three components to the visitor experience: 1. your exhibit, 2. your
product/service demonstration, and 3. your exhibit staff. You must give all three careful
thought to create an exhibit worthy of attendees time.
4. | Lead Management - If your company ever hopes to get financial ROI, and you’re not writing
orders at the show, the REAL PRODUCT of a show is leads.
5. | Measurement & Learning - What gets measured, not only gets done, but also gets
improved, and can get you positive recognition and rewards.
Instructions:
1. | The Action Planning form is only a guide and must be customized to fit your particular
organization's exhibiting program. You can add rows, change headings, change time-frames,
add/delete sections, if needed. The form has the following sections:
| a. | Trade Show Information
| b. | SMART Exhibiting Goals
| c. | Featured Products/Services
| d. | Exhibit Property/Graphics/Show Services
| e. | Pre-Show Marketing Plan
| f. | Exhibit Staff
| g. | Presentation/Demonstration
| h. | Hospitality Event
| i. | Travel Plans
| j. | Lead Management
| k. | At-Show
| l. | Post-Show
2. | Prior to starting the 16 week process:
| a. | Identify departments, business units, stakeholders and objectives. Discuss current goals
and how they can be better supported and achieved through the exhibit program.
| b. | Identify your highest and best reasons for exhibiting. Ideally, these reasons will directly
and visibly support your organization objectives. Exhibiting objectives are typically set in
the major areas of Marketing, Sales, and Relationship Management.
| c. | Convert reasons to SMART goals. A SMART goal is Specific, Measurable, Action oriented,
Realistic and Time bound. Writing goals in this format provides focus and clarity.
| d. | Create written action plans to address each SMART goal.
3. | Starting at the 16 week point, begin updating the Planning Form.
| a. | On the left-hand side are the suggested time frames for starting each section.
Read through all the sections first to familiarize yourself with the steps and time frames.
Within a section, there may be tasks listed that should be implemented in a different
time period. That different time period is colored red. These may be changed to fit
your circumstances.
| b. | Customize the tasks to meet your organization's needs for this particular trade show.
To add a row and maintain formatting, it's easier to copy and insert an existing row.
Click the row number of the row you'd like to copy, right click, select Copy.
Click the row number of where you'd like the new row inserted, right click,
select Insert Copied Cells. The spreadsheet will insert the row and move down existing
rows.
| c. | Be sure to read the Exhibit Manual carefully and insert all important due dates and order
deadlines onto the form.
4. | Be sure to use the Contacts tab to keep your vendor information in one place for easy access.
5. | It's helpful to know which competitors will be at the show, what they are bringing, and what
their messaging will be. Use the Competitors tab to capture whatever information you
can find.

## Planning Form
16 WEEK TRADE SHOW ACTION PLAN
Company Name
16 Weeks Prior to Show Date | Plan Information
|  | Prepared By | [6 empty] | Date Prepared |  |  |  | 2022-02-23
Trade Show Information
*** Read the Exhibit Manual carefully, schedule all action dates. Note deadlines for "early bird" discounts and allow lead time. ***
|  | Show Name | [6 empty] | Setup Dates/Times
|  | Show Organizer | [6 empty] | Exhibit Hall Dates/Times
|  | Show Venue | [6 empty] | Dismantle Dates/Times
|  | Booth # | [6 empty] | Budget For This Trade Show *Use Budgeting & Cost Control tool |  |  |  | 0
|  | Meeting Room # | [6 empty] | Advance Warehouse Address
|  | Target Audience Description | [6 empty] | Expected # of Target Attendees
Show Notes
SMART Exhibiting Goals Specific - Measurable - Action oriented - Realistic - Time bound
| Goal # |  | Ideally you should strive for at least three goals - you can insert rows to add more goals. | [8 empty] | Owner |  |  |  |  | Accomplished?
1
2
3
Featured Products/Services Hierarchy: 1. New Products 2. Addresses Top of the Mind Issue 3. Bread & Butter Products
|  |  | Product/Service |  |  |  |  | Features/Benefits |  |  | Show Special |  |  |  | Sales Support Materials
1
2
3
Exhibit Property, Graphics, Show Services
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Use existing exhibit, design new exhibit, order rental exhibit. Any exhibit area obstructions/limitations/restrictions? Any updates to exhibit required?
| 2 |  | Design graphics: Given spotlighted product/service and its features/benefits, what copy/graphics can best tell its story?
| 3 |  | Review Exhibitor Manual carefully noting key deadline dates.
Order show services and equipment before early bird deadline:
|  |  |  | Chairs | Carpet | Internet | Rigging
|  |  |  | Desks | Catering | Lead Retrieval | Running Water
|  |  |  | Tables | Cleaning | Lighting | Security
|  |  |  | Wastebaskets | Electrical | Material Handling | Other:
|  |  |  | Other: | Floral | Photography
[5 empty] | Forklift | Plumbing
| 4 |  | Order installation/dismantle services. If using Exhibitor Approved Contractor (EAC), review rules.
| 5 |  | Finalize shipping information and provide to vendors. (4 weeks prior)
| 6 |  | Gather supplies, credentials, travel documents, contracts, freight and service orders, return shipping forms, lead forms (if paper based) and related materials (1 week prior)
7
15 Weeks Prior | Pre-Show Marketing Plan
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Calculate Exhibit Interaction Capacity and set goal.
| 2 |  | Compile target visitor list: in-house (C/P/S) and external sources.
> Contact Sales: create Customer/Prospect/Suspect list
> Contact show organizer for pre-reg and/or post-show lists. Determine if list can be customized to only include your target audience.
| 3 |  | Complete Competitors tab to help guide marketing messaging.
| 4 |  | Create compelling marketing message and select graphic images.
| 5 |  | Design an integrated marketing campaign that delivers at least 3 direct touches to your ideal visitors. Use Email/Web/Social Media/Print/Mail, etc.
| 6 |  | Evaluate and select show marketing media and sponsorships. Use a mix of one-to-one and one-to-many media formats.
| 7 |  | Order promotional products/giveaways.
| 8 |  | Prepare press kits. (9 weeks prior)
| 9 |  | Launch pre-show marketing plan. (8 weeks prior)
| 10 |  | Maintain a list of appointments and verbal commitments. (until show time)
11
14 Weeks Prior | Exhibit Staff
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Determine staffing plan: # of staff (50 sq ft/staffer rule), department mix (sales, marketing, technical, management, other?), define roles and responsibilities.
| 2 |  | Analyze and select staffers. Draft initial staff schedule and notify staff.
| 3 |  | Order booth staff attire.
| 4 |  | Depending on the type of show, consider hiring professional talent to provide product samples, answer general questions, and/or attract attendees to your exhibit.
| 5 |  | Provide exhibit staff training with internal staff or hire professional trainer.
| 6 |  | Visit show's Exhibitor website and review educational materials, if any. Forward website link to staff, if applicable. (12 weeks prior)
| 7 |  | Schedule show staff meetings to review goals, plans, roles and responsibilities. Usually 6 to 8 weeks before the show, 1 week reminder, and day prior to opening.
| 8 |  | Put together staff preparation kit and finalize booth schedule. (6-8 weeks prior)
| 9 |  | Register all booth staff - employees and hired talent. (8 weeks prior)
| 10 |  | Conduct pre-show staff meeting and training session. (1 week prior)
11
Presentation/Demonstration
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Given spotlighted product/service and its features/benefits, how can visitors interact with the product to learn about features/benefits?
| 2 |  | Select type of presentation: Live Product/Service Demonstration, 1 to 1 or 1 to many? Theater, Video, Interactive Information Stations, Gamification, Scale Models, Other?
| 3 |  | Determine how information will be distributed: product literature, iPad stations, other?
| 4 |  | Prepare presentation staff scripts.
5
Hospitality Event
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Determine purpose of the event and date/time.
| 2 |  | Select venue and reserve.
| 3 |  | Select catering menu and entertainment.
| 4 |  | Create invitation list.
| 5 |  | Design invitation and send to invitation list. (4 weeks prior)
| 6 |  | Maintain a list of RSVPs and verbal commitments. (until show time)
7
12 Weeks Prior | Travel Plans
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Determine staff travel dates.
| 2 |  | Make air reservations.
| 3 |  | Make hotel reservations. Note cancellation penalty date.
| 4 |  | Make restaurant reservations.
5
Progress Check
| Next Actions - Add more rows if needed. | [12 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Update show budget and actual.
| 2 |  | Check on exhibit, graphics and printed materials.
3
4
8 Weeks Prior | Lead Management
| Next Actions - Add more rows if needed. | [8 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Set lead goals.
| 2 |  | Identify lead qualification criteria.
| 3 |  | Assign a lead captain to manage lead capture and follow-up.
| 4 |  | Determine how lead information will be captured (paper/electronic).
| 5 |  | Order show's lead capture system, or create a hand-held opportunity card.
| 6 |  | Determine lead follow-up plan.
| 7 |  | Create follow-up copy/graphics.
| 8 |  | Update company CRM system with lead follow-up steps.
9
Progress Check
| Next Actions - Add more rows if needed. | [12 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Update show budget and actual.
| 2 |  | Check on exhibit, graphics and printed materials.
| 3 |  | Confirm availability of product/equipment samples and technical help.
4
5
4 Weeks Prior | Progress Check
| Next Actions - Add more rows if needed. | [12 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Update show budget and actual.
| 2 |  | Check on exhibit, graphics and printed materials.
| 3 |  | Assemble your exhibit and make last minute adjustments, if needed.
| 4 |  | Check on pre-show marketing plan progress.
5
Show Time! | At-Show
| Next Actions - Add more rows if needed. | [12 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Supervise exhibit set-up. Take photos.
| 2 |  | Check on hospitality venue, catering and entertainment.
| 3 |  | Test presentation/demonstrations and practice.
| 4 |  | Conduct daily meetings with booth staff. Collect leads at end of shift or end of each day and compare to goal.
5
After | Post-Show
| Next Actions - Add more rows if needed. | [12 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Supervise exhibit dismantle.
| 2 |  | Hold a post-show recap meeting with appropriate staff. Discuss what worked, what didn't, what was learned.
| 3 |  | Enter leads into CRM system, assign to appropriate people, send requested information, begin lead follow-up.
| 4 |  | Prepare post show report with ROI forecast and lessons learned.
| 5 |  | Check on lead progress/sales conversion at three predetermined time periods. (30/60/90 or 45/90/180 days)
| 6 |  | Use Exhibiting & Financial Performance Metrics tool to analyze performance.

## Contacts
CONTACT & ACCOUNT INFORMATION
Show Name
Trade Show Information
| Show Organizer | 0 | Account Number
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Show Notes
Show Marketing/Sponsorships
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Notes
General Services Contractor
| Company Name |  | Account Number
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Notes
Exhibit Design House or Rental Company
| Company Name |  | Account Number
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Notes
Graphics
| Company Name |  | Account Number
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Notes
Freight Company
| Company Name |  | Account Number
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Notes
Temporary Staffing
| Company Name |  | Account Number
| Contact Name |  | Website
| Contact Email |  | User Name
| Contact Phone |  | Password
Date Confirmed
Notes
Hotel
| Hotel Name |  | Date Reservation Made
| Contact Name |  | Cancellation Penalty Date
| Contact Email |  | Arrival Date
| Contact Phone |  | Departure Date
Notes/Reservation #s

## Competitors
COMPETITORS
Show Name
| Prior Year | Current Year
Competitor #1
Company
Booth Size
Booth Location
Key Products Displayed:
Key Messages/Promotions:
Strengths/Weaknesses:
Why We’re Better:
Competitor #2
Company
Booth Size
Booth Location
Key Products Displayed:
Key Messages/Promotions:
Strengths/Weaknesses:
Why We’re Better:
Competitor #3
Company
Booth Size
Booth Location
Key Products Displayed:
Key Messages/Promotions:
Strengths/Weaknesses:
Why We’re Better: